## Sheet1
Activity | 2023-09-01 |  |  |  | 2023 Oct |  |  |  | 2023-11-01 |  |  | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01
| 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 |  | 2
Selection of Topic
Introduction
Literature Review
Research Methodology
Proposal Defense
System Annalysis
System Design
System prototype
Progress Presentation
Coding and Testing | bar: 2023-12-01 to 2024-03-01
Testing of the system | bar: 2024-03-01 to 2024-04-01
Implementation of the system | bar: 2024-04-01
Final Defense | bar: 2024-05-01